# 2019 CVNHP Local Heritage Grants

# APPLICATION FORM

Applications must comply with the terms of the Request for Proposals, use the format below and provide all of the information requested to be considered for review.

- Summary Page

On a single page, please provide the following information in the order shown:

Project Name/Title:

# Project Category: 2019 CVNHP Local Heritage Grants

Contact Information:

Name of Contact Person:

Authorized Signatory and Title (if different from Contact Person):

Organization:

Mailing Address:

Telephone Number:

E-mail Address:

Eligibility: Please list all active Champlain Valley National Heritage Partnership (CVNHP) and Lake Champlain Basin Program (LCBP) grants with your organization. Any organization with an existing award that has overdue workplans, reports or other deliverables is ineligible and should not apply.  Workplans for all new grant awards will be required within 45 days after receipt of your award notifications and must be initiated no more than six months after award notification.  If these deadline requirements are not met, awards may be forfeit.

A portion of the 2019 CVNHP Local Heritage grants are supported through bi-national Great Lakes Fishery Commission funds. Non-profit organizations and communities in Québec are encouraged to apply for funding.

Amount of LCBP Request: ($4,000 for an individual community or $7,500 for a regional organization)

Organization Mission Statement:

Brief Project Summary: Please describe your project in 3-5 sentences.

Project Outcome/Deliverable:  Please briefly describe measurable project outputs (3-5 sentences).

Application Content

Please include the following information (1-4) in order, using no more than 3 pages combined (12-point (or larger) Times New Roman font (or equivalent), minimum 1-inch margin on all sides).  Complete applications should be no longer than 5 pages in length (1 summary page, 3 pages for application content, 1 budget page).  Additional pages (except letters of support and participation) will not be reviewed.

Be sure to address the Request for Proposals (RFP) Selection Criteria in forming your answers in the application narrative, which should describe your project as directly and concisely as possible.  The review committee will evaluate your application based on its content in accordance with the RFP Selection Criteria.

- Describe the extent to which the proposed project involves active participation from youth and students in the research and discovery of the cultural and/or natural heritage resources associated with their community, and the creation of new artistic expressions, or interpretation of those topics utilizing fresh perspectives and/or new technology. If part of a larger project, please describe the portion of the project for which you are seeking CVNHP funding.

- List the individuals (volunteers, board member, and/or staff) and partners (organizations, state agencies, and municipalities) that will be involved in the proposed project. Briefly describe their background and qualifications. Explain how your work with other partners will enhance the effectiveness of CVNHP/LCBP funding.

- List the associated actions and tasks described pages 43-68 of the CVNHP Management Plan that the project addresses.

- Reimbursement for project expenses is linked to the receipt of task deliverables (e.g., press release, meeting notes, publication of an online guide, etc.). Use the table format below to identify specific deliverable benchmarks for your project. Identify target dates for each deliverable leading towards your project completion deadline.  If the project ends after December 31, 2019, please explain the rationale.

EXAMPLE: Project Timeline, Deliverables and Payment Schedule

| Task # | Task Title | Objective | Deliverable or Output | Timeline | Budget |
| --- | --- | --- | --- | --- | --- |
| 1 | Press Release announcing the grant award and 1st Advisory Committee Meeting | Lay out the objectives and plan for the wayside exhibits | Press release and meeting notes | 1/31/19 | $392 |
| 2 | Research and compile relevant historic information | Draft of materials for the exhibits and the brochure; purchase two alum. frames | Provide LCBP designer with complete set of graphics and 250 words text for two interpretive signs | 3/31/19 | $3,260 |
| 3 | Design exhibits and draft outline for the brochure with input of the committee and LCBP | Finalize wayside content; fabricate panels; develop draft brochure | Revised draft of three wayside exhibits and draft of brochure | 6/30/19 | $812 |
| 4 | Install the exhibits and print the brochure | Final installation of the signs and copies of the brochure | Final report, including pictures of installed signs and 30 copies of the final brochure | 10/31/19 | $532* |
|  |  |  |  | TOTAL: | $4,996 |

*Final task and deliverable must be at least 10 percent of the total budget.

C. Budget Table and Justification

Please use the format below for your budget table.

- If the CVNHP/LCBP request is part of a larger project, please indicate the estimated total project value and the funding sources.

- All expenses should be placed into one of the following major categories:

  - Direct Costs – subcategories include: Personnel (including fringe benefits), Supplies, Contracts, Equipment, and Travel.

  - Indirect Costs – Not to exceed 21% of direct costs. Include general office and operating expenses, insurance, bookkeeping, etc. Please refer to the Request for Proposals for more information about direct and indirect costs.

  - Non-federal match – While matching funds and in-kind support are not required, proposals that include a non-federal match may be considered more competitive in the grant review process. Applicants should be aware, however, that because optimal matching support may make your proposal more competitive, any match proposed will be embedded in the contact as a requirement.

- If your project includes several tasks, it is helpful for each task’s budget to be broken out separately from the other tasks.

- List additional specific expense categories where appropriate, as indicated.

- If there is more than one source of funds to be used in supporting this task, budget items should be divided by funding sources as shown in the budget table.  At a minimum, show which items will be covered by the CVNHP/LCBP grant and which items will be part of your matching contribution (if any).  List other sources of funding (if any) that are not being used as match (such as other federal funds) following your budget table as shown.

- In addition to the budget table, please include a brief justification for each line in your budget, as in the following examples:

- Project Coordinator: supports staffing for oversight of project activities, 50 hours @ $25/hr.

- Volunteers: museum docent, 25 hours @ $20/hr.

Project Budget Table Format (Dollar values for illustration purposes only.)

| Project Budget: Line Item by Task |  |  |
| --- | --- | --- |
| Line Item | Task 1 | Task 2 | Task 3 | Task 4 (Final Report - add or remove columns as needed) * | Line Item Totals for All LCBP-funded Tasks | Proposed Non-Federal Match (if any) | Line Item Totals + Proposed Match |
| Personnel | $200 | $1,500 | $250 | $250 | $2,200 | $3,000 | $5,200 |
| Fringe | $60 | $450 | $75 | $75 | $660 | $1,030 | $1,690 |
| Travel | $100 | $0 | $0 | $150 | $250 | $400 | $650 |
| Supplies | $0 | $960 | $400 | $0 | $1,360 | $1,200 | $2,560 |
| Professional Services | $0 | $0 | $0 | $0 | $0 | $1,000 | $1,000 |
| Total Direct | $360 | $2,910 | $725 | $475 | $4,470 | $6,630 |  |
| Indirect | $32 | $350 | $87 | $57 | $526 | $0 | $526 |
| TOTAL BUDGET | $392 | $3,260 | $812 | $532* | $4,996 | $6,630 | $11,626 |

* At least 10% of your total LCBP award should be reserved for the Final Report task.

D. Letters of Support

Attach any letters of participation and support to your application e-mail. Up to three letters of support may be included in your application. Please be sure that the appropriate authors sign the letters. Letters of support received separately from the application will not be included in the application review.  See the Request for Proposals for more information.

E. Submission Process

- Please your application with attached letters of support and any necessary letters of participation via e-mail to grants@lcbp.org AND jbrangan@lcbp.org.

- All applications must be submitted by 4:30 p.m. on Monday, October 1, 2018.

- NOTE: The application and budget should be submitted in Microsoft Word format. Original applications in Google Docs, formatted as a PDF, or on paper will not be accepted. Copies of letters of support, however, may be submitted as PDF documents.

Direct all questions to Jim Brangan via telephone: 802-372-0213, or e-mail: jbrangan@lcbp.org.

# Text boxes

EXAMPLE of how actions and tasks should be included in the project description:

Utilizing the medium of music and song, the “Our Heritage” project will help students from Anytown High School better understand the rich commercial heritage of Anytown (OFA Action 9.9; Task 9.9.4). In addition, Anytown High’s French Club will translate the project’s song lyrics for presentation in Montreal at the annual International Heritage Festival (OFA Action 9.9; Task 9.11.2).